## Sheet1
2012-07-07 12:54
Team Canada
To-do List
Task No. | Task | By | % Complete | Date
A | Documentation
1 | Proposal | all | 85%
2 | Design Use cases/sample reports layout | EÓL | 100% | 2012-07-02
3 | Build lookup file-postcode V ward # | EÓL | 100% | 2012-07-02
4 | Update main document with use cases | EÓL | 100% | 2012-07-02
5 | Write formal intro and content | DB | 10% | 2012-07-27
6
7
8
9
10
B | General
1 | Install MVC 4 | all | 100% | 2012-06-09
2 | Install Github plugin for Visual Studio | all |  | n/a
3 | Create MVC4 Project and upload to Git | FC | 100% | 2012-06-14
4
5
6
7
8
9
10
C | Data Modelling
1 | Create Data model in RISE | AMC | 100% | 2012-06-13
2 | Generate DB code from RISE | FC | 100% | 2012-06-14
3 | Use LINQ builder to create schema | FC | 100% | 2012-06-14
4 | Identify Excel parser | FC | 100% | 2012-07-04
5 | Write parsers for elec. and contrib. | FC |  | 2012-07-04
6 | Tidy up data formatting in Excel | FC | 100% | 2012-07-04
7 | update election data | EÓL/DB | 100% | 2012-07-05
8
9
10
D | Web API
1 | Get simple Web API working | EÓL | 100% | 2012-06-09
2 | Adding CRUD functionality | EÓL | 0% | n/a
3
4
5
6
7
8
9
10
E | MVC
1 | Design controllers | AMC |  | 2012-07-07
2 | Design views | FC
3 | Design routes
4
5
6
7
8
9
10
E | Test Driven Development
1 | Test Driven Development Demo | AMC |  | 2012-07-07
3 | Update test section of document | AMC |  | 2012-07-07
2 | Unit Test Suites | EÓL |  | 2012-07-14
4
E | Server
1 | Setup Azure account | FC | 100% | 2012-06-13
2 | Install Azure SDK | all | 100%
3 | Add new Azure website | FC | 100% | 2012-06-14
4 | Investigate data storage on Azure | DB |  | 2012-07-07
5
6
7
8
9
10
Note on B34: Fintan Costello: contributions done, check with Eoin about votes